## Sheet1
Likelyhood | Consequences
| Insignificant Risk is easily mitigated by normal day to day process | Minor Delays up to 10% of Schedule Additional cost up to 10% of Budget | Moderate Delays up to 30% of Schedule Additional cost up to 30% of Budget | Major Delays up to 50% of Schedule Additional cost up to 50% of Budget | Catastrophic Project abandoned
Certain >90% chance | High | High | Extreme | Extreme | Extreme
Likely 50% - 90% chance | Moderate | High | High | Extreme | Extreme
Moderate 10% - 50% chance | Low | Moderate | High | Extreme | Extreme
Unlikely 3% - 10% chance | Low | Low | Moderate | High | Extreme
Rare <3% chance | Low | Low | Moderate | High | High
Description | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures
Schedule creation | Effort is greater than estimated | Moderate | Moderate | Developers | Revise planned schedule and ressign human resources | Clarify the project tasks at beginning stage/ consult experienced personnel
Organisation issue | Poor project planning | Low | Moderate | Developers | Realistic planning within team | Scrum methodology
Development environment | Facilities are not available | Low | High | Developers | Backup plan/ find alternative | Regular maintenance
Development environment | No internet connection | Low | High | ISP | Identify the issue ( hardware/software) and find solution | Connect test
Development environment | Power cut off | Low | Extreme | Energy company | Identify the issue ( hardware/software) and find solution | Ensure the APS is working properly during the down time
Development environment | Flooding | Low | Extreme | Building management company | Relocate all the equipments to a safe location | Establish emergency procedure
Requirements | Requirements have been changed | Low | Moderate | Clients | Request clear new instructions with updated project time frame | Run regular meeting for project update
Personnel | Personnel need extra time to learn unfamiliar software tools or environment | Low | Low | Developers | Provide proper training | Assign proper human resource for idenvidual projects
Personnel | Personnel work slower than expected | Low | Moderate | Developers | Investigate the reason of low performance/ provide additional support to catch up the progress | Run regular meeting to review the working progress
Process | Inaccurate progress tracking results | Low | Moderate | Developers | Correct and update tracking record | Run regualr meeting to review the working progress